## Master Backlog
ID | Feature / Task | Phase | Category | Priority (P0-P3) | Complexity (S/M/L) | Est Hours | User Story / Description | Why It Matters (Sports Science / UX) | Competitors Who Do This | Dreamy Differentiation Angle | Diff Score (1-10) | Dependencies | Status | Strava API Needed | Notes
D-001 | Fix PaceTrendChart formatting bug | 1 | Bug Fix | P0 | S | 0.1 | Pace displays '8:352' instead of '8:05' — uses wrong variable in padStart() | Broken formatting destroys trust in data accuracy | All competitors display pace correctly | Table stakes fix | 1 |  | TODO | No | File: PaceTrendChart.tsx line 27
D-002 | Consolidate formatPace() — one function everywhere | 1 | Bug Fix | P0 | S | 0.5 | 4+ duplicate implementations with inconsistent behavior | Inconsistent pace display = inconsistent user experience | N/A — internal code quality | Foundation for reliable data display | 2 |  | TODO | No | Delete duplicates, import from utils.ts
D-003 | Consolidate VDOT calculation — one method everywhere | 1 | Bug Fix | P0 | S | 1 | 3 different VDOT implementations produce different results for same input | VDOT is the core fitness metric — must be trustworthy and consistent | V.O2, Runalyze, COROS all have single canonical VDOT | Single source of truth for fitness estimation | 3 |  | TODO | No | Use exponential method from vdot-calculator.ts
D-004 | Fix schema mismatches (SQLite vs Postgres) | 1 | Bug Fix | P0 | S | 1 | Strava IDs can exceed 32-bit, elevation loses precision, coachContext table missing in prod | Data loss in production is catastrophic | N/A | Data integrity | 2 |  | TODO | No
D-005 | Fix elevation profile — show actual ups and downs | 1 | Bug Fix | P0 | S | 2 | Shows only cumulative gain, not terrain profile | Elevation profile is a basic expectation on every workout detail page | Strava, Garmin, every tool shows proper elevation profile | Table stakes | 1 |  | TODO | No
D-006 | Fix EnhancedSplits — pace format + header naming | 1 | Bug Fix | P0 | S | 0.5 | Pace shows '8:3.2762', header says 'Mile Splits' but data is watch laps | Splits are a core workout review feature | All competitors | Table stakes | 1 | D-002 | TODO | No
D-007 | Fix runs-by-day chart invisible color | 1 | Bug Fix | P1 | S | 0.25 | White on white background makes one data series invisible | Chart is unusable | N/A |  | 1 |  | TODO | No
D-008 | Fix goal calculator | 1 | Bug Fix | P1 | S | 1.5 | Totally broken per user feedback | Goal setting is a core motivational feature | Garmin, COROS, Strava all have goal tracking | Table stakes | 2 |  | TODO | No | Needs investigation
D-009 | Unified color system for all charts | 1 | Code Quality | P1 | M | 3 | 4 different color approaches across charts — inconsistent visual language | Consistent design builds professional credibility and trust | Intervals.icu, Strava have consistent chart styling | Professional polish signals quality | 3 |  | TODO | No | Migrate all to workout-colors.ts or CSS variables
D-010 | Standardize time range selectors on all charts | 1 | Code Quality | P1 | S | 2 | Some charts have 1M/3M/6M/1Y, some are fixed at 12 weeks, some show all history | Inconsistent controls confuse users about what time period they're viewing | Intervals.icu has consistent selectors everywhere |  | 2 |  | TODO | No
D-011 | Chart design system — shared wrapper component | 1 | Code Quality | P1 | M | 4 | Create reusable chart component with loading states, empty states, responsive sizing, consistent tooltips | Design system reduces dev time for all future charts and ensures consistency | TrainingPeaks chart library approach | Speed of future chart development | 4 |  | TODO | No
D-012 | VDOT display consistency — clarify Training vs Estimated | 1 | Code Quality | P1 | M | 3 | 3 different VDOT storage locations, 3 different confidence calculations | Users need to trust the core fitness number — confusion kills trust | V.O2 has one canonical VDOT per athlete | Transparent confidence scoring | 5 | D-003 | TODO | No
D-013 | Remove/gate 11 test/debug pages from production | 1 | Code Quality | P2 | S | 1 | Test pages accessible in production — unprofessional |  | N/A | Professional polish | 1 |  | TODO | No
D-014 | Consolidate 10 Strava pages → 3 | 1 | Code Quality | P2 | S | 2 | 10 Strava-related pages confuse routing and maintenance |  | N/A | Code maintainability | 1 |  | TODO | No
D-015 | Delete dead code (5 files, 0 imports) | 1 | Code Quality | P2 | S | 0.5 | StravaManualConnect, strava-manual, strava-debug, /welcome, /race-predictor |  | N/A |  | 1 |  | TODO | No
D-016 | Fix hardcoded profileId: 1 in coach-tools.ts | 1 | Code Quality | P2 | S | 0.5 | CTL/ATL/TSB hardcoded to 0 — breaks multi-user support |  | N/A | Multi-user readiness | 2 |  | TODO | No
D-017 | Remove demo seed fallback secret | 1 | Code Quality | P2 | S | 0.1 | Falls back to 'demo-seed-2024' if env var missing — security risk |  | N/A | Security | 3 |  | TODO | No
D-018 | Fix silent profile ID failures — add null checks + error messages | 1 | Code Quality | P2 | S | 1 | Functions fail silently when profile ID is null |  | N/A | Debuggability | 2 |  | TODO | No
D-019 | Implement BestEfforts.tsx stub functions (4 functions) | 1 | Feature Stub | P2 | M | 4 | getBestEfforts, getBestMileSplits, getPaceCurve, getWorkoutRanking all unimplemented | Best efforts / pace curve is a flagship analytics feature | Strava, Garmin, Runalyze all show best efforts | Foundation for VDOT and PR tracking | 5 |  | TODO | No
D-020 | Implement import page activity processing | 1 | Feature Stub | P2 | M | 3 | Upload page exists but doesn't actually process or save activities | File import is critical for users migrating from other platforms | Runalyze, Intervals.icu, Golden Cheetah all support file import | Data portability | 4 |  | TODO | No
D-021 | Create missing database tables (3 tables) | 1 | Schema | P2 | S | 2 | conversationSummaries, responseCache, workoutTemplates — all blocking features | These tables are prerequisites for coach memory, caching, and workout library | N/A | Unblocks Phase 2+4 | 3 |  | TODO | No
D-022 | Encrypt stored API tokens | 1 | Security | P2 | M | 3 | Strava & Intervals.icu tokens stored as plaintext despite schema claiming encryption | Token exposure is a serious security and privacy risk | All production apps encrypt tokens | User trust / compliance | 4 |  | TODO | No
D-023 | Link planned races to race results | 2 | Race Lifecycle | P0 | M | 4 | races and raceResults tables are completely separate — no lifecycle | The plan→train→race→analyze loop is THE core user journey | TrainingPeaks, Garmin, COROS all have race lifecycle | AI coach can reference entire race history for context | 5 |  | TODO | No | Add FK, auto-match by distance+date
D-024 | Race history timeline — visual hero view | 2 | Race Lifecycle | P0 | M | 4 | Race results buried in collapsible section instead of being the centerpiece | Race history is a runner's 'career page' — should feel proud and prominent | Runalyze, Strava PR page, SmashRun badges | Beautiful timeline with VDOT overlay | 6 |  | TODO | No
D-025 | PR tracking by standard distance (5K/10K/HM/M) | 2 | Race Lifecycle | P1 | M | 3 | No unified PR tracking or progression visualization | PRs are the most emotionally significant data points for runners | Strava, Garmin, Runalyze all track PRs | PR + VDOT correlation over time | 5 |  | TODO | Yes — best_efforts
D-026 | Race calendar view with countdown + training phases | 2 | Race Lifecycle | P1 | M | 4 | No unified view showing upcoming races, past results, and training blocks | Visualizing the training cycle creates accountability and excitement | TrainingPeaks ATP view, Intervals.icu season planner | AI-enhanced race prep integration | 5 |  | TODO | No
D-027 | Training plan ↔ race wiring — generate plan from race page | 2 | Race Lifecycle | P1 | L | 6 | Schema exists but no UI for plan generation, viewing, or adherence tracking | Plan adherence is the #1 predictor of race success | Runna, TrainingPeaks, V.O2, TrainAsONE | AI generates AND adapts the plan | 7 | D-023 | TODO | No
D-028 | Bulk edit / retroactive race linking | 2 | Race Lifecycle | P2 | M | 3 | No way to clean up historical data by linking old results to workouts | Data quality compounds — clean history enables better predictions | TrainingPeaks bulk edit | One-time cleanup improves all analytics | 3 | D-023 | TODO | No
D-029 | Post-run check-in flow — standard questions after sync | 2 | Post-Run Intelligence | P0 | L | 8 | After a run syncs, coach should proactively ask: How did it feel? Analyze with full context. Suggest follow-up. | The post-run moment is when runners are most engaged and receptive to coaching | Runna has post-run AI insights; Garmin has morning report | NOBODY does contextual post-run coaching with full data awareness — this is Dreamy's killer feature | 10 |  | TODO | No
D-030 | 'Why did today feel hard?' auto-analysis engine | 2 | Post-Run Intelligence | P0 | L | 6 | Cross-reference sleep, weather, TSB, previous load, time of day, pace vs history, shoes | Understanding WHY a run felt hard is the most common coaching question | WHOOP Journal correlates variables; nobody does this for individual runs | Multi-factor explanation with ranked contributing factors — unique in the market | 9 | D-030 | TODO | No
D-031 | Explain workout difficulty — coach tool | 2 | Post-Run Intelligence | P1 | M | 3 | Coach tool that analyzes all factors contributing to perceived effort | Makes AI coaching responses data-driven rather than generic | No tool has this as a structured analysis | Unique coaching intelligence | 8 | D-031 | TODO | No
D-032 | Adaptive plan — weekly re-evaluation + diff view | 2 | Adaptive Planning | P1 | L | 8 | Plan generated once and never changes. Should re-evaluate weekly based on execution and fatigue. | Static plans fail when life happens — adaptation is the core promise of AI coaching | TrainAsONE, 2PEAK, TrainerRoad Adaptive Training, Athletica.ai | Show the user WHAT changed and WHY (transparency > black box) | 9 | D-027 | TODO | No
D-033 | Coach action approval workflow — show diff, confirm/reject | 2 | Adaptive Planning | P1 | M | 4 | When coach suggests changes, user should see what's changing and approve | Agency over your training plan builds trust and engagement | TrainingPeaks coach prescription workflow | AI suggests, human approves — best of both worlds | 7 | D-033 | TODO | No
D-034 | Progressive context collection — profile completion % | 2 | Profile | P1 | S | 3 | Smart prompts for missing information, adaptive context requests | Better context = better coaching = better outcomes | No competitor does progressive profiling well | Makes the AI smarter over time | 6 |  | TODO | No | IN_PROGRESS
D-035 | Import cadence data from Strava | 2 | Strava Integration | P2 | S | 2 | average_cadence available but not requested — needed for form analysis | Cadence + pace → stride length, a key biomechanics metric | Garmin, Runalyze, Intervals.icu all show cadence | Foundation for running economy tracking | 4 |  | TODO | Yes — streams
D-036 | Import gear_id from Strava activities | 2 | Strava Integration | P2 | S | 2 | Every activity has gear_id linking to shoes — not currently extracted | Foundation for entire shoe intelligence feature set in Phase 3 | Strava, Runalyze, SportTracks track gear | Unlocks shoe efficiency analysis | 5 |  | TODO | Yes — activity detail
D-037 | Import best_efforts from Strava | 2 | Strava Integration | P2 | M | 3 | Verified PRs (400m→marathon) with pauses excluded — gold for VDOT | Best efforts are the highest-quality input for fitness estimation | Strava shows these natively | High-confidence VDOT signals | 6 |  | TODO | Yes — activity detail
D-038 | Import activity zones from Strava | 2 | Strava Integration | P2 | S | 2 | GET /activities/{id}/zones gives HR zone breakdown for free | Validate our zone calculations or use Strava's as baseline | Strava subscriber feature | Zone accuracy | 3 |  | TODO | Yes — zones endpoint
D-039 | Implement Strava webhook for real-time sync | 2 | Strava Integration | P0 | M | 4 | Real-time activity notification instead of manual polling. Critical for rate limits. | Polling doesn't scale; webhook is required for production-grade Strava integration | All serious Strava integrations use webhooks | Instant post-run coaching trigger | 5 |  | TODO | Yes — webhook API
D-040 | Import Strava athlete stats (YTD/all-time) | 2 | Strava Integration | P2 | S | 2 | Free data: YTD totals, all-time totals, biggest efforts | Quick wins for profile richness without extra API calls | Strava shows this on athlete profile | Richer user context for coaching | 3 |  | TODO | Yes — athlete stats
D-041 | Import Strava athlete zones (HR + power) | 2 | Strava Integration | P2 | S | 1 | Respect user's pre-configured zones from Strava | Users who've set custom zones in Strava expect them to be honored | TrainingPeaks respects Strava zones | User preference respect | 2 |  | TODO | Yes — athlete zones
D-042 | Complete lap sync for remaining 392 workouts | 2 | Strava Integration | P2 | S | 1 | Rate limited at last attempt — just needs retry | Complete data = better analytics | N/A |  | 1 |  | TODO | Yes — laps endpoint | Just needs rate limit reset
D-043 | Test and fix production OAuth callback | 2 | Strava Integration | P2 | S | 1 | Middleware fix applied but untested in production | OAuth is the front door — if it's broken, nobody gets in | N/A |  | 3 |  | TODO | Yes
D-044 | Manual run entry UX — sliders + smart defaults | 2 | UX | P2 | M | 3 | Replace input fields with sliders, defaults from recent workouts | Frictionless manual entry for treadmill runs and GPS-free workouts | Nike Run Club has clean manual entry | Mobile-optimized data entry | 3 |  | TODO | No
D-045 | Restore cheaper model usage tips popup | 2 | UX | P2 | S | 1 | Pop-up tips for cheaper model usage disappeared from coach page | Users need to manage AI costs | N/A | Cost transparency | 2 |  | TODO | No
D-046 | Import grade_smooth streams + calculate GAP | 3 | Grade/GAP | P0 | L | 6 | Grade Adjusted Pace makes hilly and flat runs directly comparable | GAP is the single most important normalization for training analysis | Strava shows GAP; Garmin shows it; Sauce adds it | GAP-based training load is genuinely novel for a coaching app | 7 |  | TODO | Yes — streams
D-047 | Import Strava best_efforts for high-confidence VDOT | 3 | VDOT | P0 | M | 4 | Verified PRs (pauses excluded) as VDOT input signals — fixes the VDOT 120.8 bug class | Garbage in, garbage out — best_efforts are the cleanest performance data available | Runalyze uses race results for VDOT; V.O2 uses race entries | Multi-signal VDOT with confidence weighting is unique | 8 | D-039 | TODO | Yes — activity detail
D-048 | Import segment efforts — PR tracking on specific segments | 3 | Segments | P1 | L | 6 | Verified, pause-free data with achievement rankings | Segment PRs show improvement on specific terrain — more actionable than general PRs | Strava segments is their crown jewel | AI coach references segment trends | 5 |  | TODO | Yes — segment efforts
D-049 | GAP-based training load (TRIMP adjusted for grade) | 3 | Training Load | P1 | M | 4 | A hilly 6-miler should count for more stress than flat | Grade-adjusted load more accurately reflects physiological stress | Stryd does this via power; nobody does it via GAP | More accurate fitness/fatigue model | 8 | D-049 | TODO | No
D-050 | Import temp streams + build personal heat performance curves | 3 | Performance | P1 | M | 4 | Device-recorded temperature cross-referenced with weather API | Heat affects performance 10-20% — understanding YOUR heat sensitivity is huge | Klimat annotates weather; Stryd has air power; CORE measures core temp | Personal heat curve is unique | 7 |  | TODO | Yes — streams
D-051 | Weather-adjusted training load (heat stress index) | 3 | Training Load | P1 | M | 4 | Weight TRIMP/TSS by heat stress — 90°F easy run = harder physiologically | Stops runners from thinking they're 'getting slower' in summer | Nobody does this at the training load level | Genuinely novel load adjustment | 9 | D-053 | TODO | No
D-052 | Import cadence streams — stride length + form analysis | 3 | Biomechanics | P1 | M | 4 | Per-second cadence → stride length = pace/cadence. Track cadence drift as fatigue indicator. | Cadence drift in last miles of long runs is a key fatigue signal | Garmin running dynamics, Stryd, COROS | AI coach explains form changes contextually | 6 |  | TODO | Yes — streams
D-053 | Running economy tracking — pace at given HR over time | 3 | Performance | P0 | M | 4 | 7:30/mi at 155bpm today vs 160bpm 3 months ago = real fitness improvement | Running economy (Efficiency Factor) is more useful than VDOT for day-to-day tracking | TrainingPeaks shows Pa:HR decoupling; Stryd shows running economy | Trend over time with contextual explanation is unique | 8 |  | TODO | No | Also called Efficiency Factor
D-054 | Fatigue resistance metric — last 25% vs first 75% | 3 | Performance | P1 | M | 3 | Track pace maintenance over run duration, especially in long runs | Fatigue resistance is the #1 predictor of marathon performance | Stryd durability metric; WKO5 Stamina | Tracked over time with coach commentary | 7 |  | TODO | No
D-055 | Negative split tendency tracker | 3 | Performance | P1 | S | 2 | Track positive/negative/even split patterns by workout type | Pacing strategy is the most fixable error in race execution | Metathon does basic split analysis | Coach integration: 'You tend to go out too fast on tempos' | 5 |  | TODO | No
D-056 | Time of day analysis — circadian performance profile | 3 | Analytics | P1 | M | 3 | Build personal profile: morning vs evening performance by workout type | Knowing your best training time optimizes workout scheduling | Runalyze shows time-of-day distribution | Personalized scheduling recommendations | 5 |  | TODO | No | Uses start_date_local
D-057 | Training partner effect analysis | 3 | Analytics | P2 | S | 2 | athlete_count shows group vs solo — correlate with pace, RPE, completion | 'Your average pace is 15s/mi faster on group runs' is powerful social insight | Nobody tracks this systematically | Unique social-performance correlation | 6 |  | TODO | Yes — activity detail
D-058 | Route familiarity effect — detect repeated routes | 3 | Analytics | P2 | M | 4 | Cluster similar GPS routes, analyze performance on familiar vs new | Runners perform better on known routes (reduced mental load) | Nobody does route-performance correlation | Novel insight | 6 |  | TODO | Yes — latlng streams
D-059 | GPS route visualization with pace/HR color overlay | 3 | Visualization | P1 | L | 8 | Interactive map with pace/HR gradient, point-click detail, playback scrub | Route visualization is expected by every runner | Strava, Garmin, WorkOutDoors all show route maps | Pace coloring + elevation profile on map | 4 |  | TODO | Yes — latlng streams
D-060 | Segment discovery — find popular segments near your routes | 3 | Discovery | P2 | L | 6 | Show nearby segments on map with your best efforts and improvement trends | Gamification through segment hunting increases engagement | Strava Explore, Strava Local Legends | AI coach suggests goal segments | 4 |  | TODO | Yes — segments/explore
D-061 | Workout comparison tool — overlay pace, HR, environmental factors | 3 | Analytics | P1 | L | 6 | Compare this tempo to last 5 tempos with weather/elevation context | Comparison with context prevents false conclusions about performance | Intervals.icu has activity comparison; TrainingPeaks has workout comparison | Automatic environmental normalization in comparison is unique | 7 |  | TODO | No
D-062 | Device/watch tracking per activity | 3 | Analytics | P2 | S | 1 | Track which device recorded which activity, identify data quirks by device | Device-specific HR accuracy varies significantly | SportTracks tracks device | Data quality awareness | 3 |  | TODO | Yes — activity detail
D-063 | Pace curve / Critical Speed model | 3 | Performance | P1 | M | 4 | Best pace visualization with 42-day vs all-time overlay; Critical Speed calculation | CS is a better fitness marker than VDOT for many purposes | Stryd Critical Power, WKO5 Power Duration Curve | Running-specific CS with AI interpretation | 7 | D-019 | TODO | No
D-064 | Enhanced HR zone breakdown per activity | 3 | Analytics | P1 | M | 3 | Compare to target zones for workout type; trend zone distribution over weeks | Zone compliance tells you if you're actually training at the right intensities | Strava subscriber zones, Intervals.icu, TrainingPeaks | Target vs actual zone comparison | 5 |  | TODO | No
D-065 | Training distribution analysis — shift recommendations | 3 | Analytics | P1 | S | 2 | 'Your Threshold distribution would benefit from more Z1 volume' | 80/20 principle: most runners train too hard on easy days | Runalyze polarization analysis, Intervals.icu distribution | Actionable recommendation to shift distribution is unique | 7 |  | TODO | No
D-066 | Kudos tracking & sync from Strava | 3 | Social | P1 | L | 6 | Track who gives you kudos, how often, and engagement patterns | Social validation drives app engagement and is genuinely fun data | Strava shows kudos but doesn't analyze patterns | Social intelligence nobody else offers | 7 |  | TODO | Yes — kudos endpoint | Rate limit: 1 API call per activity
D-067 | Kudos leaderboard + engagement trend analysis | 3 | Social | P1 | M | 4 | Rank supporters, identify what activities get most engagement | Social engagement data drives sharing behavior | Nobody analyzes kudos patterns | Unique social analytics | 7 | D-073 | TODO | No
D-068 | 'Ghost kudos' detector — friends who went quiet | 3 | Social | P2 | M | 3 | Rolling window detection of supporters who stopped engaging | Fun social insight that creates conversation and re-engagement | Nobody does this | Delightful novelty feature | 6 | D-073 | TODO | No
D-069 | Comments tracking from Strava | 3 | Social | P2 | M | 4 | Import who commented and what — show highlights on workout detail | Social context enriches the workout review experience | Strava shows comments but doesn't aggregate |  | 4 |  | TODO | Yes — comments endpoint
D-070 | Social engagement dashboard — charts, trends, leaderboard | 3 | Social | P1 | L | 6 | Kudos trend, engagement rate, top friends, best time to post | A completely unique analytics view — nobody does social analytics for runners | Nothing comparable exists | 100% differentiation | 8 | D-073,D-074 | TODO | No
D-071 | Club activity feed analysis | 3 | Social | P2 | M | 4 | Show what club members are doing, trends, popular routes | Club engagement creates community and retention | Strava Clubs is basic feed | Analytical overlay on club data | 5 |  | TODO | Yes — clubs endpoint
D-072 | Strava gear sync — import gear_id + GET /gear/{id} | 3 | Shoes | P0 | M | 4 | Link every workout to specific shoes: name, brand, model, total distance | Shoe tracking is the foundation for all shoe intelligence features | Strava, Garmin, Runalyze, SportTracks all track gear | Auto-sync from Strava | 4 | D-038 | TODO | Yes — gear endpoint
D-073 | Shoe mileage dashboard with retirement alerts | 3 | Shoes | P0 | M | 4 | Per-shoe mileage by workout type, month, % toward configurable retirement threshold | Shoe retirement directly affects injury risk — worn shoes = higher impact forces | Strava, Runalyze, ShoeCycle, Garmin | Visual mileage bar + rotation suggestions | 5 | D-080 | TODO | No
D-074 | Shoe efficiency model — controlled comparison across shoes | 3 | Shoes | P0 | L | 8 | After adjusting for pace, HR, temp, elevation, fatigue, grade: which shoe produces best running economy? | No app currently isolates shoe performance from confounding variables | Stryd has basic shoe analytics; nobody controls for all variables | Flagship feature — THIS IS THE SHOE KILLER APP | 10 | D-080,D-081,D-049,D-055 | TODO | No
D-075 | Shoe rotation analysis + patterns | 3 | Shoes | P1 | M | 3 | Auto-detect which shoes for which workout types, visualize rotation | Shoe rotation extends shoe life and reduces injury risk | Nobody does rotation analysis | Unique visualization | 6 | D-080 | TODO | No
D-076 | Shoe recommendation engine — suggest shoe for tomorrow | 3 | Shoes | P1 | M | 4 | Based on workout type, mileage, efficiency data, recent usage | 'Wear the Pegasus tomorrow — save the Vaporfly for race day' | Nobody does this | AI-powered daily shoe suggestion | 8 | D-082,D-083 | TODO | No
D-077 | Shoe break-in curve — performance vs mileage accumulation | 3 | Shoes | P2 | M | 3 | Track sweet spot (many runners report 50-150mi best) and degradation | Data-driven shoe retirement instead of arbitrary mileage cutoffs | Nobody tracks break-in curves | Novel data visualization | 7 | D-080,D-082 | TODO | No
D-078 | Injury correlation by shoe | 3 | Shoes | P2 | M | 3 | Cross-reference soreness reports with shoe used and mileage | Direct connection between equipment and injury risk | Nobody correlates shoes to injury | Preventive coaching insight | 7 | D-080 | TODO | No | Requires soreness body map
D-079 | Surface type inference (trail vs road) from GPS+elevation+pace | 3 | Shoes | P2 | M | 4 | Combined with shoe data: performance by shoe × surface type | Trail miles degrade shoes differently; surface-shoe optimization | Komoot does surface detection for routing; nobody for training analysis | Novel | 6 |  | TODO | Yes — latlng streams
D-080 | Import full activity detail (calories, suffer_score, pr_count, photos) | 3 | Strava Integration | P2 | M | 3 | Selectively import rich metadata from GET /activities/{id} | Richer data enables richer analysis and more context for coaching | All serious integrations use activity detail endpoint |  | 3 |  | TODO | Yes — activity detail
D-081 | Import latlng streams (full GPS coordinates) | 3 | Strava Integration | P2 | M | 3 | Foundation for route visualization, route familiarity, segment matching, surface inference | GPS data unlocks an entire class of features | Every map-based tool ingests GPS |  | 4 |  | TODO | Yes — streams | Storage: ~10K points per activity
D-082 | Import moving streams (boolean per-second) | 3 | Strava Integration | P2 | S | 1 | Distinguish stopped time from slow pace; identify rest intervals in fartlek | Accurate moving time is essential for pace accuracy | Golden Cheetah, Intervals.icu use moving flags |  | 3 |  | TODO | Yes — streams
D-083 | Historical pattern recognition engine | 4 | Pattern Engine | P0 | L | 12 | Analyze months/years of data: 'You always struggle Day 3 of high mileage weeks', 'You PR when CTL is 50-55 and TSB is +5 to +8' | Pattern detection is what makes AI coaching actually intelligent vs generic | WHOOP Journal does basic correlation; nobody does multi-factor pattern detection for running | THE core differentiator — an AI coach that actually KNOWS you | 10 |  | TODO | No | Statistical pattern detection across all stored data
D-084 | Predictive insights — forward-looking based on detected patterns | 4 | Pattern Engine | P0 | L | 10 | 'Based on last 6 weeks, you'll PR if you race in next 10 days', 'Your current trajectory suggests 1:25 HM by April' | Predictions create accountability and excitement — and validate the coaching | Garmin race predictor is basic; COROS race predictor is basic; nobody predicts training trajectory | AI predictions backed by YOUR data patterns | 10 | D-094 | TODO | No
D-085 | Auto-generated weekly insights (3-5 personalized cards) | 4 | Insights | P1 | L | 6 | Trend alerts, 'what's different this month', surprising correlations | Proactive insights make the app feel alive vs passive logging | Garmin Morning Report is closest; Strava subscriber insights are shallow | Depth and personalization of insights is unique | 8 | D-094 | TODO | No
D-086 | Coach memory timeline — what the AI has learned about you | 4 | Coach Memory | P1 | M | 4 | Visual timeline: 'Learned you struggle in heat (June 2025)', 'Noticed you PR after down weeks' | Makes AI coaching feel personal and cumulative vs stateless | Nobody visualizes AI learning about the user | Unique transparency into AI state | 9 |  | TODO | No
D-087 | Automatic insights dashboard — dedicated page | 4 | Insights | P1 | L | 6 | Weekly insight generation, trend alerts, 3-month rolling comparison | A page you come back to every week for your 'training report card' | Runalyze has some insight features | AI-curated, not just charts | 7 | D-096 | TODO | No
D-088 | Race day countdown & prep (2 weeks before A race) | 4 | Race Prep | P1 | L | 8 | Daily tips, race checklist, weather forecast, pace band generator, nutrition reminders, course analysis, fitness prediction | Pre-race anxiety is real — structured countdown builds confidence | Garmin has basic race widget; nobody has a 2-week guided prep sequence | AI-powered race prep tailored to YOUR specific race and fitness | 8 |  | TODO | No
D-089 | Running streak & consistency tracking | 4 | Gamification | P1 | M | 3 | Streaks, consistency %, perfect weeks — gentle gamification | Consistency is the #1 factor in running improvement | SmashRun badges, Nike Run Club streaks | Tied to AI coaching: 'Great consistency this month' | 4 |  | TODO | No
D-090 | Soreness body map — tap body parts, 1-5 scale, track patterns | 4 | Health | P1 | L | 6 | Schema exists, UI doesn't. Correlate with shoes, mileage, workout type. | Early soreness detection prevents injury — the #1 reason runners quit | WHOOP has pain tracking; Recover Athletics has prehab | Correlated with shoes + training load is unique | 8 |  | TODO | No
D-091 | Wellness trends dashboard — HRV, RHR, sleep, weight, stress | 4 | Health | P1 | L | 6 | Visualization of health inputs over time from Apple Health / Intervals.icu | Understanding inputs is as important as outputs for long-term performance | Athlytic, WHOOP, Oura all do this for recovery; nobody connects to training | Wellness trends CONNECTED to training outcomes is unique | 7 |  | TODO | No | Intervals.icu import exists
D-092 | Sentiment-aware coach — dynamic tone adaptation | 4 | AI Coach | P1 | M | 4 | If user seems frustrated/anxious, adjust tone. Remember emotional patterns. | Emotional intelligence separates good coaching from data dumps | No AI coaching app adapts to emotional state | Genuinely empathetic AI | 8 |  | TODO | No
D-093 | Periodization view — Base→Build→Peak→Taper with overlays | 4 | Planning | P2 | L | 6 | Show training phases, where user is in cycle, what's coming next | Periodization is the fundamental structure of all training programs | TrainingPeaks ATP view, Intervals.icu season view | AI explains WHY you're in this phase | 6 |  | TODO | No
D-094 | Cross-training support — bike/swim/strength with equivalent stress | 4 | Cross-Training | P2 | L | 6 | Log non-run activities, calculate equivalent training stress | Hybrid athletes need unified load tracking across modalities | TrainingPeaks, Intervals.icu handle multi-sport; nobody unifies strength+endurance well | Unified stress model is the biggest whitespace in the market | 9 |  | TODO | No | Strava sends non-run activities (currently filtered out)
D-095 | Running power estimates from pace+grade+bodyweight | 4 | Performance | P2 | L | 6 | Stryd-like functionality without requiring a power meter | Power normalizes for hills, wind, and terrain — more objective than pace | Stryd requires hardware; COROS/Garmin wrist power is noisy | Accessible running power without additional hardware | 7 | D-049 | TODO | No | Requires grade_smooth streams and body weight
D-096 | Ultra marathon support — 50K to 100M | 4 | Ultra | P2 | L | 8 | Time-based training, elevation as primary metric, aid station planning, power hiking | Ultra running is the fastest growing segment of running; completely underserved by tech | Vert.run focuses on trail/ultra; nobody does AI coaching for ultras | AI ultra coaching is a blue ocean | 8 |  | TODO | No
D-097 | User preference tracking — persist to DB | 4 | Personalization | P2 | M | 3 | Learn preferred workout times, distance preferences, communication style | Personalization compounds — the more the AI knows, the better it coaches | Nobody persists user preferences for coaching context |  | 5 |  | TODO | No | Currently memory-only
D-098 | Shareable race cards — IG Story/Post/Twitter sizes | 5 | Shareability | P1 | L | 8 | Beautiful cards with finish time, VDOT, course map, splits, weather, branding | Viral growth loop — users share, friends discover Dreamy | Strava generates share cards; nobody generates ANALYSIS share cards | Share cards include AI insights, not just metrics | 7 |  | TODO | No
D-099 | Weekly recap card — shareable weekly summary | 5 | Shareability | P1 | M | 4 | Miles, runs, key workout, fitness trend, VDOT change, branding | Weekly sharing creates habitual engagement | Strava has weekly summary; Athlytic has daily | AI-curated highlight | 5 |  | TODO | No
D-100 | PR celebration cards with confetti + share button | 5 | Shareability | P1 | M | 4 | Confetti animation, old vs new PR comparison, improvement % | Celebrating wins drives retention and word-of-mouth | Strava celebrates PRs; nobody generates a share-ready PR card with context | PR card includes training journey narrative | 6 |  | TODO | No
D-101 | Milestone celebrations — lifetime miles, streaks, race count, VDOT | 5 | Gamification | P2 | M | 4 | Achievement system for non-PR milestones | Long-term engagement through milestone recognition | SmashRun badges, Nike Run Club achievements | Tied to coaching narrative | 4 |  | TODO | No
D-102 | Public profile / race resume — getdreamy.run/@username | 5 | Public | P2 | L | 6 | Optional public page: race history, PRs, VDOT chart, shoe rotation | Public profiles create organic discovery and build running identity | Strava profiles are social; nobody has a 'race resume' | Professional runner portfolio | 6 |  | TODO | No
D-103 | Route export as GPX/TCX | 5 | Export | P2 | M | 3 | Export routes with optional GAP overlay | Data portability builds trust; useful for sharing courses | Strava, Garmin export routes | GAP overlay on exported route is unique | 3 |  | TODO | Yes — routes endpoint
D-104 | Weekly email digest (or in-app digest card) | 5 | Communication | P2 | L | 6 | Miles, key workouts, trends, next week preview — delivered weekly | Re-engagement channel for users who drift away from daily use | TrainingPeaks weekly email, Strava weekly summary | AI-written personalized digest | 6 |  | TODO | No
D-105 | Apple Health integration — sleep, HRV, RHR, weight | 5 | Integration | P3 | L | 8 | Import health data for wellness trends and post-run analysis | Apple Health is the #1 health data aggregator on iOS | Athlytic, HRV4Training, many apps read Apple Health | Enriches coaching context | 5 |  | TODO | No
D-106 | Garmin Connect integration (alternative to Strava) | 5 | Integration | P3 | L | 12 | Direct Garmin import: activities, HR, sleep, HRV, Body Battery, stress | Garmin has 30%+ of the GPS watch market — not everyone uses Strava | Most analytics tools connect to Garmin | Richer health data than Strava | 5 |  | TODO | No | Garmin API is more complex
D-107 | Push notifications — workout reminders, check-ins, PRs, race countdown | 5 | Notifications | P2 | L | 8 | Service worker push for proactive coaching moments | Notifications drive habit formation and re-engagement | Nearly all mobile apps have push | Coach-driven notifications feel personal | 4 |  | TODO | No
D-108 | Full data export — CSV/JSON of all user data | 5 | Export | P2 | M | 3 | All workouts, race results, plans, conversations, assessments, shoes | Data ownership builds trust; GDPR compliance | Strava, Garmin offer bulk export | Users own their data | 4 |  | TODO | No
D-109 | API for third-party apps | 5 | Developer | P3 | L | 8 | REST API for accessing Dreamy data externally | Creates developer ecosystem — other tools build on Dreamy | Strava, Intervals.icu, TrainingPeaks have APIs | Platform play | 6 |  | TODO | No
D-110 | Transparent training load dashboard — show the math | NEW | Performance Model | P1 | L | 8 | Display CTL/ATL/TSB with customizable time constants, visible formulas, adjustable TRIMP models | Black-box scores destroy trust. Transparent models build expert users who evangelize. | TrainingPeaks (TSS/PMC), Intervals.icu (customizable), Runalyze (TRIMP), Elevate (free CTL/ATL/TSB) | Show the math AND explain it in plain English — nobody does both | 9 |  | TODO | No | Biggest whitespace per all 3 research sources
D-111 | Auto-detected threshold from workout data (no lab test needed) | NEW | Performance Model | P1 | L | 8 | Estimate lactate threshold from workout HR/pace data patterns — DFA alpha-1 or heart rate deflection | Lactate threshold is the most important training anchor. Lab tests cost $200+ and require clinic visits. | AI Endurance (DFA alpha-1), Garmin (HR deflection), COROS (HR-pace relationship), Xert (automatic FTP) | Auto-detect AND explain to user why threshold changed | 9 |  | TODO | No | AI Endurance pioneered this; massive differentiator
D-112 | Personalized recovery model — learns YOUR physiology | NEW | Recovery | P1 | L | 8 | Track how YOUR body responds to different training loads, not population averages | Individual recovery rates vary 3-5x between athletes. Population models are wildly wrong for edge cases. | AI Endurance (unique: learns individual response), WHOOP (partially personalized), Morpheus (recovery-shifted zones) | Recovery model that improves over months of data | 9 |  | TODO | No | Requires 6-8 weeks of data to calibrate
D-113 | Lifestyle-performance correlation engine | NEW | Analytics | P1 | M | 6 | 'Your tempo pace improves 2% when you sleep 8+ hours', 'Alcohol night before correlates with 15s/mi slower easy runs' | Connecting lifestyle inputs to training outputs is THE most asked coaching question | WHOOP Journal does basic correlation; nobody connects lifestyle to running-specific outcomes | Multi-factor correlation with running-specific context | 10 | D-094,D-103 | TODO | No | Requires sleep+wellness data import
D-114 | Aerobic decoupling tracking (Pa:HR drift) | NEW | Analytics | P1 | M | 4 | Track cardiac drift in second half of easy/long runs as aerobic fitness indicator | Decoupling >5% = aerobic base not big enough — actionable coaching signal | TrainingPeaks (Pw:HR), Intervals.icu (decoupling analysis), WKO5 | Plain English explanation: 'Your heart worked 8% harder in the second half — more easy miles needed' | 7 |  | TODO | No
D-115 | Interval auto-detection + scoring | NEW | Analytics | P1 | M | 4 | Algorithmically detect intervals without lap button, then score consistency/recovery/target accuracy | Most runners forget to press lap; interval quality data gets lost | Intervals.icu is the gold standard here; nobody else does it well | AI scores intervals AND feeds back into plan adjustment | 7 |  | TODO | No
D-116 | Heat acclimation protocol tracking | NEW | Environment | P1 | M | 6 | Track cumulative heat exposure and adaptation progress over 10-14 day protocol | Heat acclimation (plasma volume expansion) is the single biggest legal performance enhancer for summer racing | Garmin has heat acclimation status; CORE sensor measures core temp | Guided protocol with progress tracking is unique | 7 |  | TODO | No
D-117 | Altitude adjustment for pace/performance | NEW | Environment | P1 | M | 4 | Normalize performances across different elevations; predict sea-level equivalents | A 20:00 5K at 6000ft ≈ 19:15 at sea level — context matters hugely | V.O2 has altitude conversion, Runalyze has corrections | Automatic adjustment based on GPS elevation data | 5 |  | TODO | No
D-118 | Race execution analysis + replay | NEW | Race Analysis | P0 | L | 8 | Deep split analysis: pacing strategy grade, comparison to plan, environmental factors, what-if scenarios | The #1 post-race question: 'What happened and what should I do differently?' | Metathon does basic marathon analysis; Strava shows splits but no grading | AI grades your race execution and suggests specific pacing changes for next race | 9 | D-023,D-024 | TODO | No
D-119 | AI chat coach with FULL training context awareness | NEW | Coach AI | P0 | L | 10 | Ask questions, get answers that reference YOUR actual data, history, patterns, and upcoming plan | The ultimate differentiator: AI coaching that's as informed as a human coach who's reviewed your entire training log | No tool has an AI coach that actually knows your full data history | DREAMY'S CORE VALUE PROPOSITION — this is WHY users choose Dreamy over everything else | 10 |  | TODO | No | Already partially built; this is about deepening context
D-120 | Recovery-adjusted training zones (shift daily based on readiness) | NEW | Recovery | P1 | M | 4 | HR zones shift based on recovery status — your Zone 2 ceiling is lower when fatigued | Static zones assume you're always fresh. Daily zone adjustment prevents overtraining. | Morpheus (unique: daily shifting zones based on HRV recovery) | Dynamic zones with explanation: 'Zone 2 ceiling lowered today because HRV is down 12%' | 8 |  | TODO | No | Requires HRV/readiness input
D-121 | Real-time form degradation detection during runs/races | NEW | Form Analysis | P1 | M | 6 | Track cadence drop, GCT increase, stride length shortening as fatigue proxy during the run | Form breakdown is the first sign of pacing problems — catching it early saves races | Garmin shows running dynamics but doesn't flag degradation; Stryd shows form changes | AI explanation: 'Your cadence dropped 6% at mile 18 — this pattern preceded your wall at mile 22 last time' | 9 | D-055 | TODO | No
D-122 | Training plan adapts to BOTH biometrics AND life context | NEW | Planning | P1 | L | 8 | Integrate calendar (busy week), travel (altitude/timezone), sleep quality, social context into plan adjustments | Most adaptive plans react only to workout data. Real coaching considers the whole person. | 2PEAK uses time-budget; nobody integrates life context | The most holistic adaptive planning in the market | 10 | D-033,D-094 | TODO | No
D-123 | Race fueling calculator | NEW | Nutrition | P2 | M | 4 | Calculate carb/fluid requirements based on pace, duration, weather, body weight for a specific race | Bonking (glycogen depletion) is the most common race failure mode — avoidable with proper fueling | Precision Hydration (sweat test), MyMottiv (nutrition calculator), EatMyRide | Personalized fueling plan for YOUR race, not generic guidelines | 6 |  | TODO | No
D-124 | Unified strength + endurance load quantification | NEW | Strength | P1 | L | 8 | A heavy squat session should contribute to fatigue score so run plan adjusts tomorrow | The 'strength-endurance bridge' is the #1 whitespace identified across all research sources | TrainingPeaks handles multi-sport but not gym; Wahoo SYSTM includes yoga/strength but cycling-focused | Single systemic stress score combining running and strength — nobody does this well | 10 |  | TODO | No | Huge opportunity for hybrid athletes (Hyrox, CrossFit Endurance)
D-125 | File fidelity validation + source-of-truth selection | NEW | Data Quality | P1 | M | 6 | Detect when Strava-imported files lose power/laps; prefer Garmin originals; warn about data gaps | Silent data corruption undermines all downstream analytics | Intervals.icu explicitly warns about Strava API constraints; nobody else surfaces data quality | Transparency about data quality builds trust with data-savvy users | 8 |  | TODO | No
D-126 | Coach-athlete platform — manage athletes, shared calendar, chat | NEW | Coach | P2 | L | 8 | Multi-athlete management with AI doing analytical grunt work, human coach adds wisdom | Coach platform creates B2B revenue stream and network effects | TrainingPeaks (dominant), Final Surge (free tier), Intervals.icu (coach features) | AI handles analysis, human handles relationship — best of both worlds | 7 |  | TODO | No
D-127 | Custom alerts/rules engine | NEW | Alerts | P1 | M | 4 | Alerts when training load exceeds threshold, HRV drops below baseline, ramp rate too high | Proactive alerts prevent injury and overtraining — the most valuable coaching intervention | Intervals.icu has some alerting; myTrainingForecast does injury risk alerts | AI-contextualized alerts: not just 'load is high' but 'load is high AND you slept poorly — consider skipping today' | 8 |  | TODO | No
D-128 | Training block summary — end-of-block report card | NEW | Analytics | P2 | M | 4 | At end of a training block: what adaptations occurred, compliance %, key improvements, areas for growth | Periodic reflection drives learning and motivation | Nobody generates block-level summaries automatically | AI-written narrative of your training block story | 7 |  | TODO | No
D-129 | 'Data gap detector' with fallback load logic | NEW | Data Pipeline | P2 | M | 4 | If a run is missing HR or power, still maintain coherent load history using fallback models | Missing data shouldn't create holes in longitudinal analytics | Polar handles missing sensors gracefully | Transparent fallback with confidence flags | 6 |  | TODO | No
D-130 | 'Explain the model' UI per metric — inputs, constants, time windows | NEW | Visualization | P2 | M | 4 | For every metric, a expandable section showing exactly how it's calculated | Transparency is the antidote to black-box fatigue — and a trust moat | Runalyze documents formulas in help docs; nobody shows math inline | Click any metric → see the formula → builds expert users who trust and evangelize | 9 |  | TODO | No
D-131 | Plan compliance score — intent-aware, not just completion | NEW | Gamification | P2 | S | 3 | Did you execute the POINT of the week? Not just 'did you run 5 days' | Intensity compliance matters more than volume compliance | TrainingPeaks has compliance coloring; Intervals.icu has fuzzy matching | Intent-aware: 'You hit 100% of mileage but missed all tempo targets' | 7 | D-027 | TODO | No
D-132 | Menstrual cycle-adjusted training recommendations | NEW | Female Physiology | P2 | L | 6 | Adjust readiness, training intensity, and recovery expectations by cycle phase | Female athletes are systematically underserved by training apps that ignore hormonal variation | Wild.ai, FitrWoman — but no mainstream running app does this | Mainstream integration of female physiology — not a separate 'women's app' | 8 |  | TODO | No | Growing market demand
D-133 | Morning readiness score — HRV + sleep + subjective feel | NEW | Analytics | P2 | M | 4 | Morning check-in that combines objective metrics with subjective feel | The moment of highest coaching value: 'Should I train hard today?' | WHOOP recovery, Oura readiness, HRV4Training morning readiness, Garmin Training Readiness | Transparent model (not black box) with training-specific recommendation | 6 |  | TODO | No | Requires HRV/sleep data
D-134 | Community benchmarks — anonymous comparison to similar runners | NEW | Sharing | P2 | M | 4 | See how your training metrics compare to runners with similar goals/experience | Context makes metrics meaningful: 'Your VDOT is in the 75th percentile for first-time marathoners' | Strava does age/weight comparison on segments; nobody does training metric benchmarking | Anonymous aggregation for privacy | 7 |  | TODO | No | Requires user base to be meaningful
D-135 | Baseline calibration flow — guided assessment run | NEW | Onboarding | P1 | M | 4 | Guide new users through a calibration run to initialize VDOT, threshold, and zones accurately | Better initial data → better models → better coaching from Day 1 | COROS EvoLab requires 25-min uninterrupted run to unlock; nobody makes it a guided experience | Onboarding experience that doubles as first coaching moment | 6 |  | TODO | No
D-136 | Intervals.icu deep integration — two-way sync | NEW | Integration | P2 | M | 4 | Import wellness data, export planned workouts, sync analysis | Intervals.icu is the power user's platform — integrating captures data-nerd segment | Intervals.icu has open API + wellness writes + API cookbook | Best-of-both: Dreamy coaching + Intervals.icu analytics | 5 |  | TODO | No | Already partially built

## Competitive Landscape
Category | Tool | What They Do Well | What They Miss | Dreamy's Angle
Social Hub | Strava | Unbeatable social graph, segments, route heatmaps, massive API ecosystem | Shallow analytics, black-box Relative Effort, no coaching | Don't compete on social — integrate deeply, analyze what Strava can't
Hardware Ecosystem | Garmin Connect | Deepest physiological data from wrist (HRV, sleep, Body Battery, Training Readiness) | Black-box algorithms, no customization, no coaching layer | Ingest Garmin data, make it transparent and actionable
Hardware Ecosystem | COROS Training Hub | Wrist running power, EvoLab analytics, coach team features | Smaller ecosystem, power not comparable to Stryd | Better analytics + AI coaching on top of COROS data
Hardware Ecosystem | Polar Flow | Pioneered HRV (Nightly Recharge), explicit TRIMP framing, cardio vs muscular load separation | Dated UI, limited third-party integrations | Polar's science with modern UX + AI
Coach Platform | TrainingPeaks | Industry standard: PMC chart, TSS/CTL/ATL/TSB, massive coach ecosystem, WKO5 | Expensive, complex, no AI, dated UX, no running-specific features | AI does the analytical work coaches do manually in TP
Analytics | Intervals.icu | Best free analytics: custom charts, interval detection, API cookbook, coach chat | Cycling-first, UI complexity, no mobile app | Running-first, coaching-first, beautiful mobile UX
Analytics | Runalyze | Best running analytics: effective VO2max, marathon shape, TRIMP, race prognosis, transparent formulas | No coaching, no mobile app, donation-based sustainability | Runalyze's depth + AI coaching + beautiful UI
AI Coaching | Runna | Fastest growing: integrated strength/mobility, clean UX, Strava bundle | Plans don't deeply adapt, no analytics depth, no AI chat | Deeper personalization, pattern recognition, transparent metrics
AI Coaching | TrainAsONE | True adaptive AI: adjusts every workout based on execution | Ugly UI, limited analytics, no coaching feel | Better UX, deeper analytics, conversational coaching
AI Coaching | AI Endurance | DFA alpha-1 threshold detection, personalized recovery model, learns YOUR physiology | Small user base, limited UI | Adopt their best science ideas with superior UX and AI chat
Recovery | WHOOP | 24/7 strain monitoring, personalized recovery score, Journal correlations | Expensive subscription, hardware required, black-box scores | Software-only recovery insights that explain themselves
Recovery | Oura Ring | Best sleep staging, temperature deviation, readiness score | No training context, ring required | Connect Oura data TO training outcomes
Running Power | Stryd | Only reliable running power: CP, PDC, air power, shoe analytics | Hardware required ($250+), power data not widely understood | Estimated running power from pace+grade+weight (no hardware needed)
Desktop Analytics | GoldenCheetah | Infinitely customizable, Python/R integration, privacy-focused | Steep learning curve, desktop-only, intimidating UX | Accessibility: same depth for non-programmers
VDOT/Pacing | V.O2 (Jack Daniels) | Gold standard VDOT, training paces, altitude/heat adjustment | No analytics depth, plan marketplace model | VDOT + multi-signal confidence + AI explanation
Visualization | SmashRun | Beautiful long-history visualization, training bands, gamification | Running-only logging, no coaching, limited analytics | SmashRun's visual DNA + coaching + analytics
Beginner | Couch to 5K / NRC / Runkeeper | Accessible, audio coaching, large user bases | No depth, no personalization, no analytics | Dreamy can serve beginners AND grow with them to advanced
Tri/Multi | TriDot | EnviroNorm (heat/humidity/elevation), genetics module, tri-specific | Tri-only, expensive, controversial 'optimization' claims | Environment normalization without the tri lock-in
Biomechanics | Ochy | AI gait analysis from phone camera, 3D skeletal model | One-off analysis, not integrated into training | Integrate form insights into ongoing coaching context
Browser Extension | Elevate / Sauce for Strava | Free CTL/ATL/TSB on Strava, peak power, raw data access | Extensions only, no coaching, dependent on Strava UI | Native app with same analytics depth + AI coaching on top

## Differentiation Matrix
DREAMY'S DEFENSIBLE DIFFERENTIATORS
Differentiator | What It Means | Who Comes Closest | Why They Can't Match It
AI Coach with Full Data Awareness | Ask questions, get answers referencing YOUR training history, patterns, physiology, upcoming plan, and race goals | Garmin AI summaries, Runna post-run insights | They summarize single workouts. Dreamy reasons across your entire history.
Transparent Metrics (Show the Math) | Every metric has an expandable explanation of inputs, formulas, time constants | Runalyze documents formulas in help docs | Nobody shows the math INLINE next to the metric in the UI.
Multi-Factor 'Why Did That Happen' Engine | Cross-reference sleep, weather, TSB, shoes, time-of-day, previous load to explain any workout | WHOOP Journal correlates some variables | Nobody does multi-factor explanation for individual running workouts.
Shoe Efficiency Model (Controlled Comparison) | After adjusting for ALL confounders: which shoe actually makes you faster? | Stryd has basic shoe analytics | Nobody controls for weather, grade, fatigue, time-of-day in shoe comparison.
Weather-Adjusted Training Load | TRIMP weighted by heat stress index — hot runs count for more stress | Klimat annotates weather; nobody adjusts load | Nobody modifies the actual training load calculation based on conditions.
Pattern Recognition → Predictive Coaching | 'You PR when CTL is 50-55 and TSB is +5 to +8' → 'Race in the next 10 days' | Garmin has basic race predictor | Nobody detects YOUR personal performance patterns across months of data.
Social Intelligence (Kudos Analytics) | Who likes your runs, when they stopped, engagement trends by activity type | Strava shows kudos count | Nobody analyzes kudos PATTERNS — leaderboard, ghost detection, trends.
Unified Strength + Endurance Load | Gym sessions contribute to fatigue score, running plan adjusts | TrainingPeaks handles multi-sport | Nobody unifies strength (RPE × volume) with endurance (TRIMP) into one stress model.
Adaptive Plan with Life Context | Plan considers busy week, travel, sleep quality, not just workout data | 2PEAK uses time-budget | Nobody integrates calendar + travel + biometrics + execution into one adaptive engine.
Emotional Intelligence in Coaching | Detects frustration/anxiety, adjusts tone, remembers emotional patterns | Nobody | This doesn't exist in any endurance software.

## Strategic Priorities
STRATEGIC PRIORITIES — WHAT TO BUILD AND WHY
10 BIGGEST WHITESPACE OPPORTUNITIES
1 | Transparent, explainable training metrics | Most tools use black-box scores (Garmin Training Readiness, WHOOP Recovery). Show the math. Build expert users who evangelize.
2 | AI coaching with FULL training context awareness | No AI coach knows your complete history. This is Dreamy's entire reason for existing.
3 | Multi-factor 'Why did that happen?' analysis | Connecting sleep + weather + shoes + fatigue to explain individual workout outcomes. Nobody does this.
4 | Unified strength + endurance load quantification | The hybrid athlete (Hyrox, CrossFit Endurance) market is exploding. No tool treats strength and running as equal.
5 | Weather-adjusted performance trending and training load | Everyone annotates weather. Nobody adjusts the actual load/pace calculation for conditions.
6 | Shoe efficiency model with controlled comparison | After isolating confounders: which shoe makes you faster? Currently impossible to answer without a lab.
7 | Personalized recovery model that learns YOUR physiology | Individual recovery varies 3-5x. Population models are wrong for most people.
8 | Race execution analysis with AI grading and recommendations | Post-race analysis is THE highest-engagement coaching moment. Currently underserved.
9 | Adaptive planning that considers life context (not just biometrics) | Busy week + travel + poor sleep should change your plan. Currently no tool does this well.
10 | Pattern recognition → predictive coaching from historical data | 'You PR when CTL is 50-55 and TSB is +5 to +8' → 'Race in the next 10 days'. Unique.
10 TABLE-STAKES FEATURES (must have, don't differentiate)
1 | Strava integration (sync, display, basic analytics) | If you don't sync with Strava, you don't exist to 90% of runners.
2 | Garmin device sync | 30%+ of GPS watch market. Non-negotiable.
3 | Basic workout history / training log | The minimum viable product.
4 | HR zone visualization | Every tool shows this.
5 | Weekly/monthly volume summaries | Standard in every running app.
6 | Personal records / PR tracking | Strava, Garmin, everyone.
7 | Run mapping on activity view | If you can't show a map, you're not a running app.
8 | Training plan calendar | Some form of structured scheduling.
9 | Pace/distance/HR charts on workout detail | The basic activity review experience.
10 | Mobile-responsive web experience | Runners check stats on phones.
10 FEATURES THAT LOOK COOL BUT DON'T MATTER
1 | Wrist-based running power (COROS/Garmin) | Inconsistent, not comparable across devices, most runners don't know what to do with it.
2 | VO2max estimates from watches | Varies wildly between brands/days. False precision on an inherently noisy metric.
3 | Explorer tile games (VeloViewer, StatsHunters) | Fun but zero training benefit. Niche engagement, not core value.
4 | AI-generated activity names | Cute, not valuable. Don't waste engineering time.
5 | 500Hz raw IMU data (RunScribe-level) | Overwhelms everyone except researchers. No actionable insight for 99% of runners.
6 | Social feed features competing with Strava | You will never out-social Strava. Don't try.
7 | Detailed foot strike classification | Research shows foot strike type alone doesn't predict injury.
8 | Complex multi-component fitness signatures (Xert 3-parameter) | Impressive science but most runners can't act on it.
9 | Full nutrition tracking in a running app | Better done in dedicated apps (MyFitnessPal). Import calories via API if needed.
10 | Segment leaderboard clones | Strava owns this. Any clone is dead on arrival.
5 STRONGEST MOATS IN THE ECOSYSTEM
1 | Strava's social network (~120M users) | Network effects make this unassailable. Everyone syncs TO Strava. Don't compete — integrate.
2 | Garmin's hardware-software lock-in | Training Readiness, Body Battery, VO2max all require Garmin. 30%+ GPS watch market share.
3 | TrainingPeaks' coach ecosystem | De facto standard for coached athletes. Coaches' workflows are built around TP. High switching cost.
4 | Stryd's running power patent portfolio | No direct competitor can replicate their footpod approach. Lock-in via power-based plans.
5 | Data history accumulation | Any platform with 2+ years of your data has massive switching costs. Favors incumbents.
DREAMY'S MOAT STRATEGY
1 | AI context accumulation | Every conversation, every workout, every pattern detected makes the AI smarter. Switching means starting over.
2 | Pattern recognition depth | 6+ months of data creates predictions no other tool can replicate. The longer you use it, the better it gets.
3 | Transparent metrics philosophy | Users who understand their metrics become expert advocates. Trust > lock-in.
4 | Data portability as trust signal | Full export at any time. Users stay because Dreamy is BETTER, not because they're trapped.
5 | Vertical depth in running | Not multi-sport, not social, not hardware. The deepest AI running intelligence in the market.

## Phase Summary
Phase | Name | # Items | Est Hours | Focus | Key Outcome
1 | Fix What's Broken + Foundation | 22 | ~25h | Bug fixes, code quality, schema fixes, security | Everything that exists works correctly
2 | Core Experience Completion | 23 | ~65h | Race lifecycle, post-run intelligence, adaptive plans, Strava quality | The main user loops work end-to-end
3 | Strava Data, Social, Shoes & Deep Analytics | 37 | ~150h | GAP, best efforts, shoe intelligence, social analytics, deep performance metrics | Insights no other app provides
4 | Intelligence & Differentiation | 15 | ~85h | Pattern recognition, predictive insights, coach memory, smart features | Things only Dreamy can do
5 | Growth & Sharing | 12 | ~65h | Shareable cards, public profiles, push notifications, integrations, API | Features that help the app grow
NEW | Research-Driven Additions | ~28 | ~150h | Transparent metrics, threshold detection, personalized recovery, unified load, female physiology | Features identified from competitive audit that fill critical gaps